## Slide 1
ER-CHAI
AI-Assisted Chart Generation & Analysis Platform
Executive Summary and Proposal for Productionalization
Prepared for: Economic Research Leadership
Date: April 2, 2026 | Classification: Internal Use Only

## Slide 2
Agenda
1. Executive Summary & Value Proposition
2. Current Prototype — What Exists Today
3. Production Gaps & Architecture Assessment
4. Proposed AWS Production Architecture (with Okta IdP)
5. AI Enhancement Roadmap (3 Phases)
6. Implementation Timeline (7 Months)
7. Budget & Resource Plan (2-3 MVP Resources)
8. Risk Assessment & Mitigation
9. Success Metrics & Recommendation

## Slide 3
Executive Summary
Why ER-CHAI, Why Now
THE ASK
▸ $258,900 Year 1 investment (dev + infra)
▸ $116,760/yr recurring (0.5 FTE + AWS)
▸ 2-3 resources over 7 months
▸ Phased delivery — production value at Month 3
THE VALUE
▸ 3-5x faster chart creation vs. manual workflows
▸ AI-powered analysis, summaries, and annotations
▸ Publication-ready exports (Python, R, PDF)
▸ Secure multi-user platform for the full ER team
WHAT IS ER-CHAI?
A working prototype that lets economists create FRBSF-branded charts using natural language AI commands.
▸ Ingest data from FRED API or CSV/Excel uploads
▸ AI assistant modifies charts via conversation
▸ Vision AI replicates styling from reference images
▸ Auto-generates executive summaries
This proposal funds the move from local prototype to secure, cloud-hosted, multi-user production platform on AWS.

## Slide 4
Current Prototype
What Exists Today — Fully Functional Local Application
Component | Technology
Backend | Python 3.11+, FastAPI, uvicorn
Frontend | React 18, TypeScript, Konva.js, Zustand
Database | SQLite (aiosqlite)
AI / LLM | AWS Bedrock — Claude Sonnet 4.5
Image Analysis | OpenCV + Bedrock Vision API
Data Source | FRED API + CSV/Excel upload
Export | Python (matplotlib), R (ggplot2), PDF (ReportLab)
Tests | 211 unit + property-based tests (Hypothesis)
KEY CAPABILITIES
✦ Interactive Konva.js canvas with drag-and-drop
✦ AI chat: "Change to area chart", "Add recession bands"
✦ Reference image analysis — replicate any chart style
✦ Auto-generated executive summaries (trend, peaks, outlook)
✦ Annotations: H-lines, V-lines, V-bands, text labels
✦ Right-click context menu for font/color editing
✦ Project save/load with full state persistence
✦ FRBSF branding applied by default

## Slide 5
Production Gap Assessment
What Needs to Change for Multi-User Cloud Deployment
Component | Current State | Production Need
Compute | Single-process local | Containerized, auto-scaling (ECS Fargate)
Frontend | Vite dev server, localhost | S3 + CloudFront CDN
Database | SQLite (single-file) | Aurora PostgreSQL Serverless v2
Auth | None | Okta IdP (SAML/OIDC) via ALB
AI/LLM | Direct Bedrock, no guardrails | Prompt caching, rate limits, content filtering
Storage | Local filesystem | S3 (datasets, charts, exports)
Monitoring | Console logging | CloudWatch, X-Ray, structured logging
Security | config.yaml with creds | Secrets Manager, IAM roles, VPC
CI/CD | None | CodePipeline + CodeBuild

## Slide 6
Proposed AWS Production Architecture
Secure, Scalable, Multi-User Platform with Okta SSO
USER-FACING LAYER
☁ CloudFront CDN — low-latency delivery
☁ S3 — static frontend hosting
☁ ALB + WAF — load balancing, DDoS protection
☁ Okta IdP — SAML/OIDC SSO, MFA, RBAC
☁ ALB OIDC — JWT validation at the edge
COMPUTE & AI LAYER
☁ ECS Fargate — serverless containers, auto-scale
☁ Bedrock (Claude 4.5) — chat, vision, summaries
☁ SQS — async image analysis & PDF generation
☁ ElastiCache (Redis) — sessions, prompt cache
DATA & OBSERVABILITY
☁ Aurora PostgreSQL Serverless v2
☁ S3 — datasets, exports, chart images
☁ Secrets Manager + KMS
☁ CloudWatch Logs + Metrics
☁ X-Ray distributed tracing
☁ VPC + GuardDuty

## Slide 7
AI Enhancement Roadmap
Three Phases of Increasing Intelligence
PHASE 1: Chart Intelligence (Mo 1-3)
▸ Multi-series auto-detection — AI suggests optimal chart types
▸ Smart annotation suggestions — recession bands, policy events
▸ Comparative chart generation — overlay multiple FRED series
▸ Natural language data filtering — "Show only 2020 onwards"
PHASE 2: Advanced Analysis (Mo 3-5)
▸ Automated anomaly detection — structural breaks, regime changes
▸ Forecast overlay — ARIMA / trend extrapolation on charts
▸ Cross-dataset correlation — visual hypothesis testing
▸ Publication-ready narrative — Economic Letters, working papers
▸ Template library — curated templates for common indicators
PHASE 3: Collaboration (Mo 5-7)
▸ Shared chart workspaces — real-time multi-user editing
▸ AI review assistant — branding compliance, data accuracy
▸ Version history with AI diff — plain-language change log
▸ Batch chart generation — bulk production across districts
▸ Custom AI personas — tailored for different publication types

## Slide 8
Implementation Timeline
7-Month Phased Delivery — Production Value at Month 3
PHASE 1: Foundation & Cloud Migration (Months 1-3)
Docker + ECS Fargate | SQLite → Aurora | S3 + CloudFront
Okta SSO (SAML/OIDC via ALB) | CI/CD pipeline | CloudWatch + X-Ray
Phase 1 AI: smart chart types, annotation suggestions | WAF + VPC
PHASE 2: AI & Scale (Mo 3-5)
SQS async queue | ElastiCache
Anomaly detection, forecasting
Load testing | UAT with team
PHASE 3: Collab (Mo 5-7)
Real-time collaboration
AI review + batch generation
Training + rollout
KEY MILESTONES
✓ Month 3 — Production deployment: cloud-hosted, Okta SSO, basic AI enhancements live for early adopters
✓ Month 5 — Advanced AI: anomaly detection, forecasting, correlation analysis available; UAT complete
✓ Month 7 — Full launch: real-time collaboration, batch generation, templates, team-wide rollout

## Slide 9
Budget & Resource Plan
Lean MVP Team — 2-3 Resources
ONE-TIME DEVELOPMENT COSTS
Role | Effort | Rate | Cost
Full-Stack Lead Engineer | 1 × 7 months | $16,000/mo | $112,000
Frontend / DevOps Engineer | 1 × 6 months | $15,000/mo | $90,000
QA + Security (part-time) | 0.5 × 4 months | $14,000/mo | $28,000
Project Manager (shared) | 0.25 × 7 months | $13,000/mo | $22,750
TOTAL DEVELOPMENT |  |  | $252,750
MONTHLY AWS INFRASTRUCTURE (STEADY STATE)
Service | Monthly
ECS Fargate (2-4 tasks) | $150
Aurora PostgreSQL Serverless v2 | $120
Bedrock (Claude 4.5, ~50K req/mo) | $800
S3 + CloudFront + ElastiCache | $60
CloudWatch, WAF, Secrets Mgr, SQS | $60
Okta IdP (org license assumed) | $0*
TOTAL MONTHLY | $1,230
TOTAL INVESTMENT SUMMARY
Year 1 (Development + Infra):
$258,900
Annual Recurring (Year 2+):
$116,760/yr
Breakdown:
0.5 FTE maintenance: $90,000
AWS infrastructure: $14,760
Bedrock growth buffer: $2,000
Security/compliance: $10,000
~48% savings vs. full-team build

## Slide 10
Risk Assessment & Mitigation
Risk | Likelihood | Impact | Mitigation
Bedrock API cost overruns | Medium | Medium | Prompt caching (ElastiCache), per-user quotas, cost alerts
Bedrock model deprecation | Low | High | Abstract LLM behind service interface, support model swapping
User adoption resistance | Medium | Medium | Early UAT involvement, training sessions, champion users
Data sensitivity with Bedrock | Low | High | All data in-account, no external training, VPC endpoints
Scope creep on AI features | Medium | Medium | Phased delivery with clear acceptance criteria per phase
Okta IdP integration | Medium | Low | ALB native OIDC support minimizes custom code

## Slide 11
Success Metrics
Metric | Target | How We Measure
Chart creation speed | 3-5x faster than manual | Time-tracking comparison study
Active monthly users | 80% of ER team within 3 months | Okta login analytics
AI assistant adoption | 70% of charts use ≥1 AI command | Backend telemetry
Export volume | 50+ publication-ready exports/month | S3 / export endpoint metrics
System availability | 99.5% uptime | CloudWatch synthetic monitoring
User satisfaction | NPS > 40 | Quarterly survey

## Slide 12
Recommendation & Approval Request
We recommend proceeding with the full 3-phase implementation using a lean MVP team of 2-3 resources. The prototype has already demonstrated the core value proposition — AI-assisted chart generation significantly accelerates the workflow for economic researchers.
YEAR 1 INVESTMENT
$258,900
Development + infrastructure 7-month delivery
ANNUAL RECURRING
$116,760/yr
0.5 FTE + AWS infra Starting Year 2
TEAM STAFFING
2-3 Resources
Full-stack lead + FE/DevOps + part-time QA
Prepared by the ER-CHAI Development Team | April 2026 | Internal Use Only